## ProjectName
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Feedback Management System | 1 | Analysis | Requirement Analysis | 1 | 2018-08-04 | 2018-08-04 | 1 | 2018-08-04 | 2018-08-04 | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar | Completed
|  |  | Preparing understanding document | 1 | 2018-08-04 | 2018-08-04 | 1 | 2018-08-04 | 2018-08-04 | Abhiram Ravi,Sija Cyriac
|  |  | Updating QTS | 1 | 2018-09-17 | 2018-09-17 | 0.5 | 2018-09-17 | 2018-09-17 | Palash Jaipurkar
|  |  | Understanding HLD/Class Diagram Prep | 2 | 2018-09-18 | 2018-09-18 | 2 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar
|  | Design | Unit Test Plan Preparation | 1 | 2018-09-18 | 2018-09-18 | 1.5 |  |  | Sija Cyriac,Anup Raj
|  |  | LLD Preparation | 3 | 2018-09-18 | 2018-09-18 | 3 |  |  | Shweta,Sushmita Singh
|  |  | UTP Review | 0.5 | 2018-09-18 | 2018-09-18 | 0.5 |  |  | Sushmita Singh,Shweta
|  |  | UTP Rework | 1 | 2018-09-18 | 2018-09-18 | 1 |  |  | Sija Cyriac,Anup Raj
|  |  | LLD Review | 1 | 2018-09-18 | 2018-09-18 | 1 |  |  | Palash Jaipurkar,Abhiram
|  | Build | Coding | 6 | 2018-09-19 | 2018-09-19 | 6 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar | Completed
|  |  | Code Self Review | 3 | 2018-09-19 | 2018-09-19 | 3 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar | Completed
|  |  | Self Testing | 2 | 2018-09-19 | 2018-09-19 | 2 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar | Completed
|  |  | Rework | 3 | 2018-09-19 | 2018-09-19 | 3 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar | Completed
|  |  | Code Peer Review | 4 | 2018-09-19 | 2018-09-19 | 4 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar | Completed
|  |  | Peer Testing | 5 | 2018-09-20 | 2018-09-19 | 5 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar
|  |  | Test Result review | 2 | 2018-09-20 | 2018-09-20 | 2 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar
|  |  | Rework | 1 | 2018-09-20 | 2018-09-20 | 1 |  |  | Anup Raj,Abhiram Ravi,Sija Cyriac,Shweta,Sushmita Singh,Palash Jaipurkar
|  |  | Code Integration | 2 | 2018-09-20 | 2018-09-20 | 2 |  |  | Anup Raj, Abhiram Ravi
|  |  | Integration Testing | 1 | 2018-09-20 | 2018-09-20 | 1 |  |  | Sija Cyriac,Palash Jaipurkar
|  |  | Rework | 1 | 2018-09-20 | 2018-09-20 | 1 |  |  | Sushmita Singh,Shweta
|  |  | Test Result review | 1 | 2018-09-20 | 2018-09-20 | 1 |  |  | Anup Raj
|  |  | Total Planned Hrs : |  |  | Total Actual Hrs: | 41.5